WELLNESS LODGE

Website and Reservation System

End-to-End Delivery, Launch and Operational Handover Checklist

From project initiation and .com.pg registration through fully operational handover

| Document Owner | Project Lead |
| --- | --- |
| Business Owner | Wellness Lodge Management |
| System Owner | Appointed Systems Administrator |
| Document Date | 8 September 2026 |
| Status | Working delivery and acceptance checklist |

# Contents

# End-to-End Delivery, Launch, and Operational Handover Checklist

Document owner: Project Lead

Business owner: Wellness Lodge Management

System owner after handover: Appointed Systems Administrator

Last updated: 8 September 2026

Review cadence after launch: Weekly for the first month, then monthly and after every major change

# Purpose

This checklist takes the project from the first business decision through design, development, testing, deployment, staff training, go-live, and ongoing operation of a fully functional website and reservation system.

An item is complete only when the work is finished, checked by the responsible person, and supported by the evidence named in the checklist. A page that looks finished is not enough: reservations, availability, payments, notifications, security, backups, staff procedures, and recovery must all work together.

# Roles Used in This Checklist

| Role | Main responsibility |
| --- | --- |
| Lodge Owner / Management | Approves business rules, prices, policies, content, accounts, and go-live |
| Project Lead | Controls scope, schedule, approvals, risks, and acceptance |
| Developer | Builds, secures, tests, documents, deploys, and fixes the system |
| Front Desk | Handles reservations, guest communication, arrival, changes, and cancellations |
| Accounts / Finance | Verifies money received, refunds, payment evidence, and reconciliation |
| Systems Administrator | Manages accounts, domain, hosting, backups, monitoring, and support after handover |
| Content Approver | Confirms wording, photos, room information, policies, and contact information |
| Test Users | Perform guest, front-desk, finance, and management acceptance tests |

# Completion Status

Use one status for every item: Not Started, In Progress, Blocked, Ready for Review, or Accepted. Record the responsible person, target date, completion date, evidence link, and any issue or decision beside each phase in the project tracker.

# Phase 1 — Project Initiation and Authority

Owner: Project Lead

Output: Approved project charter, authorised contacts, and controlled project workspace

☐  Appoint the Lodge Owner or authorised management representative who can approve business decisions and accept the final system.

☐  Appoint the Project Lead and confirm who may instruct the developer.

☐  Appoint the future Systems Administrator and a backup administrator.

☐  Nominate one Front Desk representative and one Accounts representative for workflow decisions and testing.

☐  Complete and sign the project/system administrator appointment and authorisation document.

☐  Confirm the official lodge legal name, trading name, registration details, physical address, postal address, telephone numbers, and authorised signatories.

☐  Confirm the target public domain name and at least one fallback domain.

☐  Confirm the project's approved budget, payment milestones, target date, and what is excluded.

☐  Define the launch scope: public website, booking engine, staff portal, bank-transfer receipt upload, notifications, reports, and any payment gateway included at launch.

☐  List later-phase items separately so they cannot be mistaken for launch requirements.

☐  Create the official project folder, source-code repository, decision log, issue register, and document register.

☐  Record who owns each digital account; business-critical accounts must be owned by the lodge, not solely by a developer or personal email address.

☐  Agree how approvals will be documented: signed document, email, or accepted project-tracker item.

☐  Agree the change-control process for new requests affecting cost, delivery date, security, reservations, or payments.

Acceptance gate: Management has signed off the authority, scope, owners, budget, and acceptance method.

# Phase 2 — Resolve the Final Technical Architecture

Owner: Project Lead and Developer

Output: One approved architecture with no conflicting build instructions

The planning material contains two architecture directions: a Firebase-based reservation platform and the current repository's Railway/Render, Next.js, PostgreSQL, and Drizzle configuration. The project must select one final production architecture before reservation development continues.

☐  Compare the two options against cost, available skills, offline/PWA needs, reporting, backups, vendor support, security, and long-term administration.

☐  Choose and document one production system of record for rooms, reservations, payments, users, and audit history.

☐  If selecting the current repository design, approve Next.js + managed PostgreSQL/Drizzle + Railway as primary hosting and Render as the alternative.

☐  If selecting Firebase, approve Firebase Hosting, Firestore, Authentication, Functions, Storage, Cloud Messaging, App Check, and Security Rules, and revise repository/deployment documents accordingly.

☐  Do not operate PostgreSQL and Firestore as competing reservation sources unless a separately approved synchronization design exists.

☐  Confirm where room photos and uploaded payment receipts will be stored.

☐  Confirm the authentication method, email provider, push-notification method, monitoring provider, DNS provider, and backup method.

☐  Produce the final system diagram showing guest, public website, booking service, database, receipt storage, email/push service, staff portal, payment provider, and monitoring.

☐  Record estimated one-time and monthly operating costs, renewal dates, billing owner, and service limits.

☐  Record data locations and third-party processors for guest personal information and uploaded receipts.

☐  Obtain management approval of the architecture, operating cost, and service ownership.

Acceptance gate: One approved architecture is reflected consistently in the architecture document, repository, deployment plan, quotation, and handover register.

# Phase 3 — Business Rules and Reservation Policy

Owner: Lodge Management

Consulted: Front Desk, Accounts, Developer

Output: Signed reservation rules used by both software and staff

## Property and inventory

☐  List every physical room with a unique internal room number or code.

☐  Define room types and map every physical room to exactly one room type.

☐  Record maximum adults, children, total occupancy, bedding, amenities, accessibility features, and active/inactive status.

☐  Decide whether guests book a specific physical room or a room type from pooled inventory.

☐  Define which rooms may be taken out of service and who may block or reopen them.

☐  Define check-in and check-out times, early/late rules, minimum stay, maximum stay, and same-day booking cutoff.

## Rates and charges

☐  Approve base nightly rates in PGK, including whether GST is inclusive or additional.

☐  Define child rates, extra-person charges, add-ons, discounts, seasonal rates, group rates, and promotional codes.

☐  Define how partial days, extensions, shortened stays, no-shows, and late checkout are charged.

☐  Require the system to store money as integer toea or another fixed-precision type, never binary floating point.

☐  Require every accepted booking to preserve its quoted rate, charges, taxes, total, and policy version so later price changes do not rewrite history.

## Availability and booking states

☐  Approve the complete status model, allowed transitions, responsible roles, and effect on availability.

☐  Recommended booking states: Draft/Quote, Awaiting Review, Held, Awaiting Payment, Confirmed, Checked In, Checked Out/Completed, Cancelled, Expired, and No-show.

☐  Recommended payment states: Unpaid, Receipt Submitted, Under Review, Part-paid, Paid, Rejected, Refund Pending, Part-refunded, and Refunded.

☐  Define exactly which booking states block room availability.

☐  Define whether a bank-transfer request immediately holds inventory or requires Front Desk acceptance first.

☐  Define when the 12-hour pay-at-front-desk hold starts. Recommended: when Front Desk accepts the request, not when the guest first submits it.

☐  Define automatic expiry time, reminder timing, extension authority, and what happens when payment arrives after expiry.

☐  Define treatment of telephone, walk-in, corporate, complimentary, and agent reservations.

☐  Require all booking channels to update the same availability source.

## Payments, cancellations, and refunds

☐  Approve deposit percentage or full-payment requirement and payment due dates.

☐  Approve accepted payment methods: bank transfer, pay at front desk, and any approved online gateway.

☐  Define who may view receipts, verify bank deposits, mark a payment paid, reject evidence, or issue a refund.

☐  State clearly that an uploaded receipt is payment evidence, not proof that cleared funds were received.

☐  Require Accounts to verify the deposit against the bank record before the system marks it paid.

☐  For online payments, require secure server-to-server gateway confirmation before marking the payment successful or locking dates as paid.

☐  Define cancellation windows, fees, no-show treatment, refund calculations, refund approval limits, and processing times.

☐  Require adjustments and refunds to create auditable records; do not overwrite the original payment history.

☐  Define daily reconciliation between accepted payments, payment records, bookings, and bank/gateway settlements.

## Guest service and privacy

☐  Approve required guest fields and avoid collecting unnecessary sensitive information.

☐  Approve terms and conditions, privacy notice, cookie notice if required, cancellation policy, house rules, and consent wording.

☐  Define retention periods for guest records, receipts, logs, and backups.

☐  Define who may export guest information and how access is approved and recorded.

☐  Define the escalation path for complaints, suspected fraud, privacy incidents, overbooking, and system outage.

Acceptance gate: Management, Front Desk, and Accounts sign the rules; every software status and deadline has an operational meaning and owner.

# Phase 4 — Client Information, Content, and Asset Collection

Owner: Content Approver

Output: Complete, accurate, legally usable content pack

☐  Complete the client information and content checklist in the submission package.

☐  Supply approved logo files in high-resolution and transparent formats.

☐  Supply original, properly licensed photographs for rooms, exterior, reception, dining, wellness facilities, amenities, local area, and staff where approved.

☐  Identify each photo, room, caption, display order, and any required credit.

☐  Supply final room names, descriptions, amenities, capacity, rates, and availability limitations.

☐  Supply approved lodge introduction, history, values, wellness services, nearby attractions, and guest information.

☐  Supply official telephone, WhatsApp, email, physical address, postal address, map pin, directions, social links, and operating hours.

☐  Supply bank name, account name, account number, branch, currency, transfer reference instructions, and payment contact through a secure channel.

☐  Have two authorised people verify bank details independently before publication.

☐  Supply check-in/out times, house rules, payment terms, cancellation/refund rules, child policy, accessibility details, and emergency contacts.

☐  Confirm whether testimonials and guest images have permission for publication.

☐  Record missing items, responsible person, due date, and approved temporary placeholder if any.

☐  Compress and resize website images while retaining archived originals.

☐  Obtain written approval for all final copy, images, rates, contact details, policies, and bank instructions.

Acceptance gate: No unapproved placeholder, guessed price, sample bank detail, or unlicensed image remains in the launch content.

# Phase 5 — Business-Owned Accounts, Domain, DNS, and Email

Owner: Systems Administrator

Output: Lodge-controlled digital services with recovery and billing configured

☐  Create or verify the official business email used as owner of GitHub, hosting, database, DNS, email delivery, monitoring, and payment services.

☐  Enable multi-factor authentication on every administrator account.

☐  Store recovery codes in an approved secure location accessible to two authorised lodge representatives.

☐  Complete the digital accounts and handover register: service, URL, account owner, recovery email/phone, billing owner, renewal date, MFA method, and access level.

☐  Confirm .com.pg eligibility, naming match, current fee, form, and submission method directly with PNGUoT before payment.

☐  Obtain the company documents, authorised signatures/seal, local-presence information, and at least two nameservers required for the application.

☐  Submit the domain application and record the submission date, receipt, contact person, follow-up date, approval, and renewal date.

☐  Prepare and approve a fallback domain plan in case .com.pg approval is delayed or unavailable.

☐  Configure DNS through the approved provider and document every record.

☐  Create role-based mailboxes such as reservations@, accounts@, admin@, and support@ instead of relying on one person's mailbox.

☐  Configure SPF, DKIM, and DMARC; test outbound delivery and replies with major email providers.

☐  Configure mailbox forwarding, retention, storage quota alerts, and backup/continuity procedures.

☐  Ensure a full mailbox cannot block receipt submission; website receipt upload remains the primary path and email is fallback.

☐  Do not place passwords, API keys, database URLs, or bank credentials in the repository or handover document.

## 5A — Prepare the .com.pg application

Important distinction: PNGUoT registers/delegates the .com.pg domain. Google Cloud DNS does not register .com.pg; it hosts the DNS zone and supplies the authoritative nameservers that must be written on the PNGUoT application.

☐  Confirm the intended name, normally wellnesslodge.com.pg, with Management in writing.

☐  Search the official .pg WHOIS service at https://whois.nic.pg/ and retain dated evidence of the result.

☐  Email PNGUoT DNS at dns@pnguot.ac.pg to confirm that the name is available and that registration is currently being accepted.

☐  Ask PNGUoT to confirm the current application form, policy, fee, renewal period, required supporting documents, acceptable payment evidence, and expected processing time.

☐  Download the current .com.pg/.net.pg application form and policy from https://www.pnguot.ac.pg/icts-dns/; do not reuse an undated local copy without checking the official page.

☐  Review the policy and confirm that the applicant has the legal right to use the requested name.

☐  Prepare the applicant's full legal organisation name, postal address, business registration number, and supporting registration/incorporation evidence.

☐  Nominate an Administrative Contact authorised to represent the lodge and provide name, address, phone, and email.

☐  Nominate a Technical Contact responsible for DNS and provide name, address, phone, and email.

☐  Select New Domain Name and .com.pg on the form; use Re-delegation only for an existing domain moving to different nameservers.

☐  Do not sign Section C until the authorised signatory has reviewed the completed form, policy, requested name, and nameserver information.

## 5B — Create Google Cloud DNS and obtain the nameservers

☐  Create a lodge-owned Google Account or Google Workspace administrator account; do not use the developer's personal account as the sole owner.

☐  Create a dedicated Google Cloud project, for example wellness-lodge-production, under the lodge's billing ownership.

☐  Link an approved billing account and configure budgets/spending alerts; Cloud DNS is a paid Google Cloud service even though the cost is normally small.

☐  Give two authorised administrators access and enable MFA; grant only the roles required to administer billing and DNS.

☐  Enable the Cloud DNS API in the selected Google Cloud project.

☐  Open Network services → Cloud DNS → Create zone.

☐  Choose Public zone.

☐  Enter an internal zone name such as wellness-lodge-com-pg.

☐  Enter the DNS name exactly as wellnesslodge.com.pg.; check spelling carefully before creating it.

☐  Keep DNSSEC Off for the initial delegation unless PNGUoT confirms the required DS-record process. DNSSEC can be enabled through a controlled change after basic delegation works.

☐  Create the zone and record the automatically generated SOA and full NS set.

☐  Do not edit, shorten, substitute, or create your own Google nameservers. Copy exactly the nameservers assigned by Google, including every one shown.

☐  Record the nameservers in the account register and take a dated screenshot/export as evidence.

☐  Resolve each assigned nameserver hostname to its current IP address for the application form if PNGUoT still requires IP fields; confirm with PNGUoT whether these dynamically managed addresses are required.

☐  Before filing, add at least one harmless public record such as a temporary verification TXT record so the new zone can be checked externally.

☐  Confirm the zone's NS and SOA records answer publicly. The PNGUoT form notes that required DNS records must be visible on the primary and secondary nameservers before processing.

## 5C — Complete and file the PNGUoT application

☐  In Section A, type the full legal organisation name, postal address, business registration number, Administrative Contact, and Technical Contact.

☐  In Section B, type the exact requested domain and the Google Cloud DNS primary and secondary nameserver hostnames; include the tertiary server and remaining Google-assigned servers where the form/PNGUoT permits.

☐  Enter nameserver IP addresses only after checking them, and never invent a fixed IP; ask PNGUoT how it wants Google Cloud's managed nameservers represented.

☐  Have a second person compare the requested domain and every nameserver entry with the Google zone character by character.

☐  Have the authorised applicant complete, sign, date, and seal Section C as applicable.

☐  Attach the requested business registration/incorporation and authority documents.

☐  Based on the official PNGUoT page checked on 8 September 2026, arrange the K300 registration fee to the published UNITECH Trust Fund account; re-confirm the amount and banking details immediately before payment.

☐  Use a clear payment description/reference agreed with PNGUoT and retain the bank-generated payment confirmation.

☐  Have Accounts independently verify payee name, account, amount, and approval before releasing funds.

☐  Scan/export a clear final application and check every page, signature, seal, attachment, and payment receipt.

☐  Email the complete application package to dns@pnguot.ac.pg from the authorised business email with a clear subject containing the requested domain and applicant name.

☐  Request acknowledgement of receipt, application/reference number, any missing requirements, and expected decision date.

☐  Save the sent email, application, attachments, receipt, acknowledgement, and subsequent correspondence in the controlled domain folder.

☐  Add follow-up dates to the project tracker. If acknowledgement is not received, follow up using the official telephone contacts published by PNGUoT.

☐  Respond to clarification requests through the authorised contact and record all corrections; do not submit conflicting forms from different people.

## 5D — Verify approval and delegation

☐  Obtain written approval/delegation confirmation from PNGUoT.

☐  Check the official .pg WHOIS record and confirm the domain, registrant/contact details where published, nameservers, and status.

☐  Query the parent delegation from at least two independent networks/tools and confirm it lists the exact Google Cloud DNS nameservers.

☐  Query the authoritative Google nameservers directly for SOA, NS, and the temporary TXT record.

☐  Check for lame delegation, spelling mistakes, missing nameservers, inconsistent answers, or DNSSEC failure.

☐  Allow for DNS propagation and TTL caching; record the time each test first succeeds.

☐  If nameservers must change later, use PNGUoT's official re-delegation form and a controlled DNS migration plan; do not delete the old zone until the change is proven worldwide.

## 5E — Connect the production website to the domain

☐  Add wellnesslodge.com.pg and www.wellnesslodge.com.pg to the production hosting service.

☐  Obtain the exact verification and routing records from the active host (Railway primary or the approved alternative). Do not copy generic example IP addresses.

☐  In Google Cloud DNS, add the host verification TXT/CNAME record exactly as provided.

☐  Add the apex A/AAAA, CNAME, ALIAS-equivalent, or host-specific record required for wellnesslodge.com.pg.

☐  Add the host-provided CNAME for www and choose one canonical address; configure the other address to redirect permanently.

☐  Use a short TTL during initial cutover, then increase it after stable verification.

☐  Wait for the host to validate the domain and issue its TLS certificate.

☐  Test http://, https://, apex, and www; confirm all routes reach the correct production site and HTTP redirects to HTTPS.

☐  Confirm the certificate covers both names, has a valid chain, auto-renews, and does not expose a staging/origin hostname.

☐  Update application URL, authentication callbacks, email links, sitemap, canonical metadata, allowed origins, gateway callbacks/webhooks, and monitoring to the final domain.

☐  Remove temporary verification records only when the issuing service confirms they are no longer required.

## 5F — Configure Google Workspace or the approved email service

☐  Decide separately whether Google is providing only Cloud DNS or also paid Google Workspace email. Cloud DNS alone does not create mailboxes.

☐  If using Google Workspace, create the Workspace subscription under lodge ownership and start domain verification.

☐  Add Google's domain-verification TXT record to Cloud DNS and wait for Workspace to verify ownership.

☐  Create named administrator accounts and role mailboxes/aliases such as reservations@wellnesslodge.com.pg, accounts@wellnesslodge.com.pg, admin@wellnesslodge.com.pg, and support@wellnesslodge.com.pg.

☐  Add the current MX records shown in the Google Workspace Admin console; use the provider-generated values rather than an old checklist.

☐  Inventory every authorised sender, including Google Workspace and the website's transactional email provider.

☐  Publish one consolidated SPF TXT record that covers all authorised senders; never create multiple separate SPF records at the root.

☐  Generate DKIM in each sending service, add its selector TXT/CNAME record to Cloud DNS, enable signing, and verify it passes.

☐  After SPF and DKIM have been working for at least 48 hours, publish DMARC initially in monitoring mode with a controlled reporting mailbox.

☐  Review DMARC reports for at least one week, correct legitimate senders, then move gradually to quarantine/reject according to an approved plan.

☐  Configure forwarding, groups, aliases, retention, storage quotas, recovery contacts, and mailbox-capacity alerts.

☐  Test sending and receiving with Gmail and non-Gmail accounts; confirm replies, attachments, spam placement, SPF, DKIM, and DMARC results in message headers.

☐  Verify website transactional email can send as the approved subdomain/address and that bounces/complaints are monitored.

☐  Document the fallback if Google Workspace or the booking mailbox is unavailable; the reservation system's private receipt upload must continue to work.

## 5G — Create the final DNS record register

Complete this register using actual provider values before go-live:

| Purpose | Name/host | Type | Value/target | TTL | Source/approver | Verified date |
| --- | --- | --- | --- | --- | --- | --- |
| Google authoritative DNS | Domain apex | NS | Google-assigned set | Provider default | Google Cloud / Systems Admin |  |
| Website apex | Blank/apex | Host-required | Production host value | Cutover value | Railway/approved host |  |
| Website www | www | CNAME | Production host target | Cutover value | Railway/approved host |  |
| Host ownership check | Host-specified | TXT/CNAME | Host-generated token | Provider default | Production host |  |
| Workspace verification | Host-specified | TXT | Google-generated token | Provider default | Google Workspace |  |
| Incoming email | Blank/apex | MX | Current Workspace/provider values | Provider value | Email provider |  |
| SPF | Blank/apex | TXT | Consolidated authorised senders | Provider value | Systems Admin |  |
| DKIM | Provider selector | TXT/CNAME | Provider-generated key | Provider value | Each sender |  |
| DMARC | _dmarc | TXT | Approved staged policy | Provider value | Systems Admin |  |
| Transactional email | Provider-specified | TXT/CNAME/MX | Provider-generated values | Provider value | Email provider |  |

## 5H — Domain, DNS, and email acceptance evidence

☐  Approved PNGUoT application, policy acknowledgement, supporting documents, payment receipt, submission email, acknowledgement, and approval are filed.

☐  Google Cloud project ID, billing owner, IAM owners, zone name, assigned NS set, and DNS export are recorded.

☐  WHOIS and parent delegation show the correct Google nameservers.

☐  Website resolves on apex and www, redirects consistently, and serves a valid HTTPS certificate.

☐  Email sends and receives, and independent header checks pass SPF and DKIM; DMARC reporting is active.

☐  Production host verification, authentication callbacks, transactional email, monitoring, and booking links use the final domain.

☐  Calendar reminders exist for .com.pg biennial renewal, Google Cloud billing, Workspace renewal, certificate monitoring, and quarterly DNS/account review.

☐  Two lodge-authorised administrators can access and recover PNGUoT correspondence, Google Cloud, Workspace/email, hosting, and monitoring.

Acceptance gate: The lodge can independently access, recover, and pay for every production service; domain and email test successfully.

# Phase 6 — Project and Development Environment Setup

Owner: Developer

Output: Reproducible, protected development workflow

☐  Confirm the selected codebase and archive superseded ZIP copies so developers do not edit different versions.

☐  Create the business-owned GitHub repository and protect the main branch.

☐  Add an appropriate .gitignore; verify that .env, secrets, uploads, database dumps, and temporary files are excluded.

☐  Run secret scanning before the first push and remove/rotate any exposed credential.

☐  Commit dependency lockfiles and document supported Node.js and database versions.

☐  Create separate local, test, staging, and production environments.

☐  Use separate databases, storage locations, email modes, keys, and domain names for staging and production.

☐  Create .env.example containing variable names and safe explanations only.

☐  Configure continuous integration to install locked dependencies, lint, type-check, test, build, and scan dependencies.

☐  Configure preview/staging deployment; do not connect a development branch directly to production.

☐  Define pull-request review, merge, release, rollback, and emergency-fix procedures.

☐  Record schema-migration rules and require tested forward and rollback/recovery plans.

☐  Verify a fresh developer can clone the repository, configure safe local variables, create the schema, seed test data, and start the application using the documentation.

Acceptance gate: A clean checkout builds consistently, CI passes, secrets remain external, and staging is isolated from production.

# Phase 7 — Data Model, Integrity, and Audit Design

Owner: Developer

Consulted: Front Desk and Accounts

Output: Approved schema and transaction design

☐  Model physical rooms, room types, amenities, photos, rate plans, restrictions, out-of-service blocks, and availability.

☐  Model guests and bookings with unique references, dates, occupancy, source/channel, status, policy version, and timestamps.

☐  Model immutable booking charge lines for room nights, taxes, discounts, add-ons, fees, and adjustments.

☐  Store currency explicitly as PGK and values as integer toea/fixed precision.

☐  Model payment attempts and receipts separately from the booking so multiple attempts, partial payments, rejection, and refunds are preserved.

☐  Store receipt file metadata, secure storage path, upload time, submitter, review status, reviewer, review time, rejection reason, and checksum if supported.

☐  Model holds with start, expiry, extension, released time, reason, and responsible user.

☐  Model users, roles, sessions, failed login attempts, password reset, disabled accounts, and last access.

☐  Model audit events for booking creation, changes, status transitions, room moves, payment decisions, cancellations, exports, and administrative settings.

☐  Include created/updated timestamps and actor identifiers on business-critical records.

☐  Define database constraints for positive rates, valid date ranges, occupancy limits, unique booking references, supported currency, and permitted values.

☐  Use database transactions and appropriate locking/constraints to prevent two concurrent requests from selling the same inventory.

☐  Treat check-out as an exclusive boundary so a room can be rebooked on the previous guest's check-out date if policy permits.

☐  Define idempotency protection for double clicks, network retries, webhook retries, email retries, and background jobs.

☐  Preserve historical bookings when rooms, rates, bank instructions, or policies later change.

☐  Define indexes for availability searches, booking lookup, staff filters, payment review, expiry jobs, and reporting.

☐  Define retention, archival, deletion/anonymisation, and legal-hold procedures.

☐  Create migration and seed data using fictional test guests and non-production bank details.

Acceptance gate: Schema review proves availability integrity, fixed-precision money, historical traceability, controlled status transitions, and auditable payment handling.

# Phase 8 — User Experience and Interface Design

Owner: Developer / Designer

Approved by: Content Approver and Front Desk

Output: Approved responsive designs and workflow prototypes

☐  Create the site map and navigation for Home, Rooms, Room Detail, Book, Booking Confirmation, Booking Lookup/Manage, About, Gallery/Experiences if included, Contact, Policies, and staff pages.

☐  Design mobile first, then tablet and desktop layouts.

☐  Create a consistent design system for colours, typography, spacing, buttons, forms, cards, tables, alerts, status badges, and empty/error/loading states.

☐  Make room price, capacity, availability, inclusions, exclusions, and policy links clear before the guest submits.

☐  Design the booking flow: dates and guests → available rooms → quote → guest details → payment choice → review and consent → confirmation.

☐  Show the exact total, currency, due amount, due time, booking reference, and next action.

☐  Design receipt upload with file requirements, progress, success confirmation, replacement rules, and staff review status.

☐  Design staff queues for new requests, expiring holds, receipt reviews, arrivals, departures, cancellations, failures, and overdue follow-ups.

☐  Keep alert acknowledgement, reservation action, and task completion as separate actions.

☐  Design PWA installation guidance only if PWA remains in the approved scope.

☐  Do not rely on background browser audio alone; combine visible outstanding queues, push notifications where approved, and repeating in-app audio while the app is open.

☐  Provide keyboard navigation, visible focus, form labels, helpful errors, colour contrast, image alternatives, and screen-reader-friendly status updates.

☐  Design slow-network, offline, duplicate-submit, expired-session, payment-pending, unavailable-room, and maintenance states.

☐  Obtain approval on the clickable prototype or staging pages before completing all screens.

Acceptance gate: Guest and staff representatives can complete their main workflows from the design without developer explanation.

# Phase 9 — Public Website Build

Owner: Developer

Output: Complete, fast, accessible marketing website

☐  Build the shared header, navigation, footer, contact actions, policy links, and responsive layout.

☐  Build the Home page with approved lodge identity, key benefits, authentic images, and booking call to action.

☐  Build Rooms and Room Detail pages from the system of record, including capacity, amenities, rate display, and availability entry point.

☐  Build About, Contact, map/directions, Gallery, Experiences, FAQ, house rules, privacy, and booking/cancellation policy pages as included in scope.

☐  Ensure telephone, email, map, WhatsApp, and social links work on mobile and desktop.

☐  Optimise images, fonts, loading order, caching, and page metadata.

☐  Add descriptive page titles, descriptions, canonical domain, social sharing metadata, robots rules, and sitemap.

☐  Add accessible forms with server-side validation, spam protection, rate limiting, and safe success/error messages.

☐  Prevent contact forms or logs from exposing personal data or internal errors.

☐  Add analytics only after management approves the provider, consent approach, and data collected.

☐  Check all copy, prices, policies, room data, bank details, image rights, spelling, and contact information against signed source material.

Acceptance gate: All approved public pages pass content, responsive, accessibility, link, performance, and security review on staging.

# Phase 10 — Reservation Engine Build

Owner: Developer

Output: Transaction-safe end-to-end booking workflow

☐  Validate check-in, check-out, guest count, room capacity, booking window, restrictions, and required fields on the server.

☐  Reject past dates, zero-night stays, reversed dates, over-capacity requests, inactive rooms, malformed input, and unsupported currency.

☐  Calculate rates and charges on the server from approved data; never trust a total sent by the browser.

☐  Produce a quote with expiry, itemised nights/charges/discounts/tax, total PGK, and policy version.

☐  Recheck price and availability inside the final booking transaction.

☐  Prevent concurrent overlapping bookings/holds at the database level or through a proven transactional locking strategy.

☐  Generate an unpredictable unique public booking reference without exposing sequential internal IDs.

☐  Add idempotency so double-clicking or retrying cannot create duplicate reservations or charges.

☐  Store the original quote snapshot and accepted terms with the booking.

☐  Create the correct hold and expiry according to the approved start trigger.

☐  Display a confirmation page that distinguishes request received, room held, payment pending, and fully confirmed.

☐  Send the guest acknowledgement and staff alert only after the booking transaction commits.

☐  Provide secure guest lookup/manage access without revealing whether unrelated email addresses or references exist.

☐  Allow permitted changes and cancellation while recording the previous values, actor, reason, financial effect, and notification result.

☐  Release inventory reliably on expiry/cancellation and make the operation safe to retry.

☐  Build scheduled checks for expiring/expired holds, pending payments, and notification retry.

☐  Provide a controlled staff override for exceptional cases with reason and audit record.

☐  Test simultaneous bookings for the final room; exactly one may succeed when only one unit remains.

Acceptance gate: Automated and manual tests prove correct price, availability, concurrency, retry, expiry, cancellation, and historical behaviour.

# Phase 11 — Payment Evidence and Online Payment Handling

Owner: Developer

Approved by: Accounts

Output: Secure, auditable payment workflow

## Bank transfer at launch

☐  Show approved bank instructions from controlled settings, not hard-coded copies scattered across pages.

☐  Show booking reference, exact PGK amount, deadline, and upload instructions.

☐  Accept only approved receipt types and enforce file-size limits.

☐  Validate file signature/content as well as extension; rename files safely and block executable content.

☐  Store uploads privately; never expose a guessable public file URL.

☐  Authorise receipt access to only permitted staff and Accounts roles.

☐  Scan uploads for malware if supported by the approved platform.

☐  Record upload, replacement, review, rejection, approval, download/view, and responsible user in the audit trail.

☐  Allow Accounts to enter bank reference, amount received, value date, notes, and verification result.

☐  Prevent Front Desk from marking payment cleared if role policy reserves this for Accounts.

☐  Handle underpayment, overpayment, duplicate transfer, unreadable receipt, wrong booking reference, and payment after expiry.

☐  Notify the guest when evidence is received, approved, rejected, or requires action.

☐  Confirm the booking only according to the approved payment and inventory rules.

## Gateway integration if included

☐  Complete bank merchant onboarding and obtain test/live credentials through approved channels.

☐  Use the gateway's hosted/tokenised payment experience so card details do not enter lodge systems unless explicitly required and certified.

☐  Verify webhook signature, event type, merchant account, currency, amount, booking reference, and payment status server-side.

☐  Make webhook processing idempotent and safe for duplicates, reordering, and delays.

☐  Record the raw gateway event securely with sensitive fields redacted, plus processing outcome.

☐  Reconcile captured, failed, reversed, refunded, disputed, and settled amounts.

☐  Never treat the browser redirect/success page alone as proof of payment.

☐  Complete gateway sandbox testing, certification, production-key ceremony, low-value live transaction, refund test, and settlement reconciliation.

Acceptance gate: Accounts can trace every paid or refunded amount from source evidence/gateway event to payment record, booking, and reconciliation report without altering history.

# Phase 12 — Staff Portal and Operational Controls

Owner: Developer

Approved by: Front Desk, Accounts, Management

Output: Role-controlled daily operating system

☐  Implement staff sign-in, logout, password reset, session expiry, MFA if approved, and account lock/rate limits.

☐  Implement least-privilege roles such as Front Desk, Accounts, Manager, and Systems Administrator.

☐  Require separate named accounts; do not use a shared reception password.

☐  Build the dashboard for new requests, outstanding receipt reviews, expiring holds, arrivals, departures, occupancy, and failed tasks.

☐  Build booking search/filter by reference, guest, date, room, status, payment status, and channel.

☐  Build booking detail with guest contact, stay details, price snapshot, payment history, receipt review, messages, and audit timeline.

☐  Allow authorised staff to create walk-in/telephone bookings using the same availability and pricing controls.

☐  Allow permitted room moves, date changes, occupancy changes, extensions, cancellations, check-in, check-out, and no-show marking.

☐  Recalculate changes as a new adjustment and preserve original amounts; never silently replace historical charges.

☐  Build room/rate/content/settings management with validation, approval controls where needed, and audit records.

☐  Block dangerous deletion of rooms, users, bookings, payments, and audit records; use deactivate/archive and controlled reversal.

☐  Build daily arrivals/departures, room occupancy, pending payments, payment reconciliation, cancellations, and management summaries.

☐  Protect CSV/PDF exports with permission checks and record exports containing personal or financial information.

☐  Provide visible failure/retry states for emails, push alerts, scheduled jobs, uploads, and gateway events.

☐  Record who acknowledged an alert, who acted, what action occurred, and when the issue was completed.

Acceptance gate: Each role can perform authorised duties and is demonstrably blocked from unauthorised financial, personal-data, and administrative actions.

# Phase 13 — Notifications and Communication

Owner: Developer and Systems Administrator

Approved by: Front Desk

Output: Reliable, monitored guest and staff notifications

☐  Create approved templates for request received, hold accepted, payment instructions, receipt received, receipt rejected, payment confirmed, booking confirmed, reminder, expiry, change, cancellation, refund, pre-arrival, and post-stay messages.

☐  Include booking reference, dates, room, amount/status, contact channel, and clear next action; exclude unnecessary sensitive details.

☐  Configure verified sending domain and production sender/reply-to addresses.

☐  Test email authentication, delivery, reply handling, bounced mail, suppression, spam placement, and mailbox capacity.

☐  Record notification attempts, provider response, delivery/failure state, retry count, and final outcome.

☐  Retry temporary failures safely without sending uncontrolled duplicates.

☐  Put permanently failed guest/staff notifications into a visible action queue.

☐  Configure PWA push only with user permission, correct device subscriptions, unsubscribe handling, and expired-token cleanup.

☐  Test staff alerts with app open, backgrounded, closed, logged out, device offline, and notification permission denied.

☐  Keep the outstanding work visible in the staff portal even if sound, email, or push notification fails.

☐  Publish an outage communication process and fallback telephone/manual booking procedure.

Acceptance gate: All critical messages have been received on real test mailboxes/devices, failures are visible, and staff know the fallback.

# Phase 14 — Security, Privacy, and Resilience

Owner: Developer and Systems Administrator

Accountable: Lodge Management

Output: Signed pre-launch security and recovery record

☐  Enforce HTTPS, secure cookies, HSTS when safe, and approved security headers.

☐  Keep all secrets in managed environment/secret storage and restrict who can view or change them.

☐  Rotate credentials used during development before production launch.

☐  Enforce server-side authorisation on every staff action, upload, export, and API route; hiding a button is not access control.

☐  Validate, normalise, and limit all input; use parameterised database access.

☐  Protect against cross-site scripting, request forgery, injection, path traversal, insecure file access, open redirects, and session fixation.

☐  Rate-limit login, password reset, contact, booking, lookup, upload, and gateway endpoints.

☐  Add bot/spam controls that do not block legitimate low-bandwidth guests.

☐  Configure database encryption in transit, restricted network access where supported, least-privilege credentials, and encryption at rest.

☐  Remove personal data, receipt contents, credentials, tokens, and full gateway payloads from normal application logs.

☐  Define log access, retention, alerting, and secure deletion.

☐  Run dependency, secret, code-quality, and vulnerability scans; assess and resolve material findings.

☐  Perform manual authorisation tests between every role and attempt direct URL/API access.

☐  Test common web-security risks and upload abuse in staging.

☐  Configure automated database and receipt-storage backups at the approved frequency and retention.

☐  Complete a restore drill into an isolated environment and record recovery time, recovered point, and any missing data.

☐  Define recovery point objective, recovery time objective, incident contacts, breach response, credential rotation, and service-status communication.

☐  Ensure at least two authorised people can access domain, hosting, database, email, and monitoring during an emergency.

Acceptance gate: No unresolved critical/high security issue; backup restore is proven; incident and recovery owners accept their responsibilities.

# Phase 15 — Complete Testing and User Acceptance

Owner: Project Lead

Responsible: Developer and Test Users

Output: Signed test report and defect register

## Automated and technical checks

☐  Run locked dependency installation, lint, type-check, unit tests, integration tests, migration tests, and production build.

☐  Test all calculations at zero, minimum, normal, maximum, boundary dates, leap dates, month/year boundaries, and timezone boundaries.

☐  Test database constraints, transaction rollback, partial failures, retries, duplicate requests, and concurrent final-room booking.

☐  Test migration from a clean database and against a production-like copy with sensitive data removed.

☐  Test supported browsers and common Android/iPhone/tablet/desktop sizes.

☐  Test low bandwidth, high latency, offline interruption, refresh/back, duplicate click, expired session, and service outage.

☐  Run accessibility, broken-link, performance, SEO, and security checks.

## Guest acceptance journeys

☐  Find a room, review details, enter valid dates and guest count, receive an accurate quote, submit, and receive acknowledgement.

☐  Attempt unavailable dates, over-capacity booking, invalid dates, malformed contact information, and duplicate submission.

☐  Upload a valid receipt, replace it if permitted, and receive correct review notifications.

☐  Submit invalid type, oversized, corrupted, duplicate, and malicious test files and confirm safe rejection.

☐  Use booking lookup/manage access and confirm another guest's data cannot be discovered.

☐  Change or cancel a booking according to policy and verify inventory, money, messages, and audit record.

## Staff and finance acceptance journeys

☐  Create telephone/walk-in booking; accept/decline request; extend/release hold; review receipt; confirm payment; confirm booking.

☐  Process partial/over/late payment, rejected receipt, cancellation, refund, room move, no-show, check-in, and checkout.

☐  Verify two staff members cannot create overlapping reservations during a race.

☐  Verify unauthorised roles cannot view receipts, confirm money, refund, manage users, alter settings, or export data.

☐  Reconcile a test day from booking/payment sources to the daily report and bank/gateway totals.

☐  Simulate email, storage, database, gateway, and scheduled-job failure; confirm errors are visible and recoverable.

☐  Test backup restoration and the documented manual outage process.

## Defect and acceptance control

☐  Classify defects by severity and business impact.

☐  Block launch for any defect that risks double-booking, wrong price, false payment status, data exposure/loss, inability to recover, or unavailable critical workflow.

☐  Retest every fix and run targeted regression tests plus the final full quality gate.

☐  Record evidence: test case, environment, build/commit, tester, date, expected result, actual result, screenshot/log, and disposition.

☐  Obtain signed UAT acceptance from Management, Front Desk, Accounts, and Systems Administrator.

Acceptance gate: All launch-blocking defects are closed and all required roles sign UAT for the exact release candidate.

# Phase 16 — Production Preparation and Go-Live

Owner: Project Lead and Systems Administrator

Output: Controlled, reversible production release

☐  Freeze the approved release candidate and record repository commit, build number, schema migration, configuration version, and deployment owner.

☐  Approve the launch date/time, change window, communication list, support coverage, and rollback decision-maker.

☐  Confirm the production hosting plan, database/storage capacity, billing method, spending alerts, and renewal ownership.

☐  Create production database, storage, email, monitoring, and keys with least privilege.

☐  Load only approved rooms, rates, policies, bank details, staff accounts, and content.

☐  Remove all sample rooms, test users, test bookings, placeholder contacts, sandbox credentials, and temporary access.

☐  Apply production migrations and verify schema version before accepting traffic.

☐  Configure the final domain and DNS with low-risk change planning; verify DNS resolution and automatic HTTPS.

☐  Verify canonical URLs, redirects, sitemap, robots rules, social previews, email links, and return/callback URLs use the production domain.

☐  Verify SPF/DKIM/DMARC and production sender reputation configuration.

☐  Enable uptime, error, database, storage, backup, certificate, domain-renewal, mailbox-quota, failed-job, and billing alerts.

☐  Take and verify the pre-launch backup/snapshot.

☐  Write the exact rollback steps for application, configuration, database migration, DNS, and communications.

☐  Place a temporary booking pause/maintenance message if cutover could create inconsistent inventory.

☐  Deploy the release, apply migrations, run smoke tests, and confirm health checks.

☐  Complete a real low-value end-to-end reservation using a controlled test room/date; verify guest message, staff alert, receipt/payment process, confirmation, reporting, cancellation/refund if appropriate, and audit trail.

☐  Confirm no real inventory was left blocked and reverse/refund the live test correctly.

☐  Obtain the final go-live decision from the authorised business owner.

☐  Record separately: local checks, CI result, staging UAT, production deployment, and live production verification.

Acceptance gate: The approved release is live on the final domain, a controlled live booking works end to end, monitoring/backups are active, and rollback remains available.

# Phase 17 — Staff Training and Operational Readiness

Owner: Project Lead

Responsible: Developer, Front Desk Lead, Accounts Lead

Output: Trained staff and signed readiness record

☐  Prepare concise role-based manuals for Front Desk, Accounts, Management, and Systems Administrator.

☐  Train Front Desk to handle new requests, alerts, holds, phone/walk-in bookings, changes, arrivals, departures, cancellations, no-shows, and guest communication.

☐  Train Accounts to review receipt evidence, verify bank deposits, record partial/over payments, reject evidence, process/record refunds, and reconcile daily.

☐  Train Management to review occupancy, revenue/payment status, cancellations, staff actions, and unresolved exceptions.

☐  Train Systems Administrator to manage users, MFA, environment settings, deployments, DNS, email, monitoring, backups, restoration, renewals, and incidents.

☐  Demonstrate that receipt upload is primary and email is the fallback; demonstrate what to do when email, internet, or the website is unavailable.

☐  Run scenario-based practice using the UAT cases without developer intervention.

☐  Confirm staff understand that acknowledging an alert does not accept the booking or complete the task.

☐  Give staff a quick-reference escalation list with names, roles, telephone/email, severity, and response expectation.

☐  Issue individual accounts and remove temporary trainer/developer access not required after handover.

☐  Record attendance, competency gaps, retraining actions, and signed readiness.

Acceptance gate: Front Desk and Accounts complete normal and exception workflows independently; administrator completes a recovery exercise.

# Phase 18 — Formal Handover and Acceptance

Owner: Project Lead

Accountable: Lodge Management

Output: Lodge-controlled, documented, accepted system

☐  Inventory and hand over the final approved requirements, architecture, policies, designs, source code, migrations, test report, training material, runbook, and warranties/support terms.

☐  Hand over the digital account register without placing passwords in the document.

☐  Verify live access for the lodge's named owners to GitHub, hosting, database, DNS, domain registration, email, storage, monitoring, analytics, and gateway accounts.

☐  Transfer billing and recovery contacts to lodge-controlled details.

☐  Record production domain, service plans, renewal dates, recurring cost, data region, support contacts, and cancellation/export procedure.

☐  Record the final deployed commit/build, schema version, configuration baseline, DNS records, and backup schedule.

☐  Provide current known issues, accepted limitations, deferred features, workarounds, responsible person, and target resolution.

☐  Define the warranty/defect period, support hours, severity levels, response targets, approved support channel, and chargeable change process.

☐  Revoke obsolete developer, contractor, test, shared, and temporary access; verify remaining least-privilege access.

☐  Take the handover backup and confirm the lodge can retrieve documentation during an outage.

☐  Complete the project handover document and obtain signatures from Project Lead, Systems Administrator, and authorised Management.

☐  Obtain final business acceptance only after the live system and all operational controls meet the agreed criteria.

Acceptance gate: The lodge owns and can operate, recover, pay for, and support the system without dependency on one individual.

# Phase 19 — Hypercare: First 30 Days After Launch

Owner: Systems Administrator

Consulted: Developer, Front Desk, Accounts

Output: Stable production operation and closed launch issues

## Daily for the first two weeks

☐  Review uptime, application errors, failed logins, failed jobs, email delivery, push failures, upload errors, storage use, database health, and unusual traffic.

☐  Review new reservations, duplicates, expiry behaviour, availability discrepancies, missing alerts, and abandoned booking patterns.

☐  Reconcile booking payments against bank/gateway transactions and investigate every difference.

☐  Confirm backups completed and no credential/domain/certificate/billing alert is outstanding.

☐  Review staff questions and update training material or safe UX wording where necessary.

## Weekly during the first month

☐  Meet with Front Desk, Accounts, Management, and technical support to review incidents and workflow friction.

☐  Report bookings received, confirmation rate, abandoned requests, average confirmation time, failed notifications, payment exceptions, cancellations, and availability incidents.

☐  Prioritise fixes by guest impact, financial risk, security, and operational workload.

☐  Apply changes through staging, tests, approval, controlled deployment, and live verification.

☐  Perform a sample trace from guest request through booking, payment evidence, staff action, confirmation, report, and audit record.

☐  Confirm the manual outage pack, contact list, and escalation contacts remain current.

☐  Close hypercare only after management accepts system stability and ownership transfers to normal support.

# Phase 20 — Ongoing Operation and Maintenance

Owner: Systems Administrator

Accountable: Lodge Management

## Every day

☐  Review outstanding reservation and payment queues, arrivals/departures, expiring holds, failed messages/jobs, and service alerts.

☐  Reconcile payments and resolve unmatched, partial, duplicated, refunded, or late transactions.

☐  Follow the manual outage process if availability cannot be trusted; enter controlled manual bookings into the system after recovery with audit notes.

## Every week

☐  Review room availability blocks, rate changes, website content accuracy, mailbox capacity, staff accounts, errors, and suspicious activity.

☐  Confirm scheduled backups succeeded and investigate any failure immediately.

☐  Review unresolved guest complaints, overbooking risks, receipt-review delays, and system exceptions.

## Every month

☐  Apply reviewed dependency/security updates through staging and the full quality gate.

☐  Review role access and disable leavers or unnecessary access promptly.

☐  Review hosting/database/storage/email usage and costs against budget and service limits.

☐  Test a sample restore or verify backup integrity according to the recovery schedule.

☐  Reconcile management reports to booking and payment detail; document and correct root causes of differences.

☐  Export/archive records only according to the approved retention and privacy policy.

## Quarterly

☐  Perform an access review signed by Management.

☐  Run a full recovery exercise covering database, receipt files, configuration, DNS contacts, and communications.

☐  Review security findings, incident history, audit logs, payment controls, privacy retention, performance, and capacity.

☐  Review business rules, rates, policies, room inventory, photos, contact details, bank instructions, and email templates.

☐  Review whether gateway, PWA, reporting, or other deferred functions are still justified and approve them through change control.

☐  Reconfirm support contacts, service ownership, billing, and renewal schedule.

## Annually and before renewals

☐  Renew domain, DNS/hosting/database/email/gateway services, certificates if not automatic, and software/service agreements.

☐  Verify domain registrant, business email, billing details, authorised signatories, and recovery contacts.

☐  Review disaster recovery objectives, data retention, privacy notice, terms, cancellation/refund rules, insurance, and merchant requirements.

☐  Conduct a complete end-to-end live controlled booking and reconciliation test.

# Mandatory Exception Procedures

| Scenario | Immediate action | Owner | Required record |
| --- | --- | --- | --- |
| Website or database unavailable | Stop relying on displayed availability; use the controlled manual log, time-stamp requests, avoid promising rooms until availability is verified, and escalate | Front Desk Lead | Incident and manual booking log |
| Suspected double booking | Freeze changes to affected inventory, contact guests privately, escalate to Management, arrange approved remedy, and correct through an audited workflow | Lodge Manager | Incident, decision, guest communication, compensation |
| Receipt uploaded but deposit not found | Keep payment under review, contact guest, do not mark paid, and recheck using approved bank evidence | Accounts | Review notes and guest message |
| Money arrives after hold expired | Do not silently reinstate; verify availability, obtain authorised decision, then confirm or refund with audit record | Accounts + Front Desk | Decision and payment/refund record |
| Wrong bank details displayed | Disable payment instructions immediately, preserve evidence, notify Management/Accounts, assess affected guests, correct centrally, and rotate/secure settings | Systems Administrator | Security/financial incident report |
| Gateway says success but webhook missing | Keep payment pending, query gateway server-side, avoid duplicate charge, and reconcile before confirmation | Accounts + Technical Support | Gateway investigation log |
| Email/push alert failed | Keep the item in the visible staff queue, use the fallback contact method, and investigate delivery without duplicating booking actions | Front Desk | Failed notification and follow-up record |
| Guest requests correction/deletion of data | Verify identity, follow approved privacy/retention rules, preserve legally required financial/audit records, and record the decision | Management | Privacy request register |
| Staff member leaves | Disable access immediately, revoke sessions/keys, transfer open work, and review recent administrative actions | Systems Administrator | Offboarding checklist and access review |
| Suspected account or data breach | Preserve logs, contain access, rotate credentials, activate incident response, assess notification obligations, and communicate only through authorised persons | Management + Systems Administrator | Incident timeline and decisions |

# Final Definition of “Fully Functional and Handed Over”

The Wellness Lodge website and reservation system is complete only when all statements below are true:

☐  The approved public website is live on the final domain with accurate content, working contact channels, HTTPS, and acceptable mobile performance/accessibility.

☐  Guests can find available rooms, obtain an accurate PGK quote, submit one reservation without duplication, upload payment evidence or use the approved gateway, and receive clear status communication.

☐  Concurrent and repeated requests cannot oversell the last available room.

☐  Front Desk can manage the full reservation lifecycle, including telephone/walk-in bookings and exceptions.

☐  Accounts can verify, reconcile, adjust, and refund payments with fixed-precision amounts and an immutable audit trail.

☐  Roles prevent unauthorised access to guest information, receipts, payment decisions, exports, settings, and user administration.

☐  Notifications, queues, scheduled expiry, monitoring, and failure handling work in production.

☐  Backups run automatically and a restore has been successfully demonstrated.

☐  All launch-blocking tests and UAT are accepted for the exact production release.

☐  A real controlled live booking has been verified end to end after deployment.

☐  Staff are trained, support and outage procedures are available, and role owners have accepted their duties.

☐  The lodge owns and can recover every critical account, and no single developer or staff member is the only access holder.

☐  Final source code, documentation, credentials handover process, account register, known issues, recurring costs, and renewals are accepted in writing.

If any one of these conditions is false, the project may be deployed or in pilot use, but it should not be described as fully functional and handed over.